## Everyday
Trefriw Community Council Community Plan for the year 2026/27
Our vision is to make Trefriw a great place to live, work and visit
Our everyday business
Task | Cost to TCC | Funding stream | Action for TCC | Date of next action
Bins and rubbish
Work with CCBC to ensure adequate street and dog bins are located in the areas most needing them | Nil | N/A | Work with CCBC | Ongoing
Biodiversity
Duty to seek to maintain and enhance biodiversity |  |  | To conduct an annual review of the Policy as adopted in May 2021. Policy reviewed and adopted in May 2026 | Ongoing as a live document but to be formally reviewed no later than May 2028
Budget setting and audit
Have a clear and costed budget for each Financial Year | Precept request for £28,169.75 submitted to CCBC for 2026/27 | Built in to the annual Precept received from CCBC | Set a budget for 2027/28 for full Council approval and submit to CCBC within set timescales. | November 2026
Budget and accounts to be subjected to appropriate scrutiny | Projected Budget of £43,107.55 for 2026/27 | Built in to the annual Precept received from CCBC | Clerk/RFO to prepare monthly income/expenditure records for scrutiny by Councillors. Clerk/RFO to prepare for scrutiny by Councillors bank reconciliations either monthly or quarterly based on account activity. Clerk/RFO to prepare quarterly cashbook for scrutiny by Councillors. To complete an annual audit for scrutiny by Councillors and onward submission to Audit Wale Office within set timescales. 2025/26 Audit projected to be approved by Council on 9th June 2026 and submitted to Audit Wales. | Ongoing Ongoing Ongoing Awaiting Audit Decision
Bus Shelters
Financial reserve set up to manage the condition of the bus shelters | TBC as required - £1,000 held in Reserves | TCC Reserve | TCC is required to manage the condition of the bus shelters in the village : six-monthly visual check and cleaning (brush /wash down) carried out. | Inspection and clean to be undertaken in October 2026
Cemetery
Provision of graves in village cemetery | No | Costs for plot and associated documents met by family/representatives of the deceased | The TCC clerk, as burial clerk, manages the required certificates and other records to allocate graves, and works closely with the funeral directors involved. | Ongoing
Maintenance of cemetery grounds | Budget of £3,050 allocated for 2026/27 to be offset by any income received from cemetery fees (unable to accurately predict level of fees that will be received annually). Budget of £6,675.00 allocated for extension works. | Built in to the annual Precept received from CCBC | Contract for main cemetery grounds maintenance (2025-2028) - awarded 12th November 2024 to commence 1st April 2025. New Tender document for cemetery extension field approved by Council on 8th October 2024. 3 year contract for cemetery extension field maintenance (2025-2028) -awarded 12th November 2024 to commence 1st April 2025. Proposed works specification for cemetery extension tender under consideration. | Ongoing
Christmas Festivities
Provide a Christmas tree and lights for the village annually | Budget of £400 allocated for festivities in 2026/27 | Built in to the annual Precept received from CCBC | Source a Christmas tree for the Christmas period 2026, replacements lights purchased in 2023. | October 2026
Community "tree lights switch on" in partnership with Trefriw Outdoors - provision of drinks and mince pies | Projected spend of up to £200 and included within overall festivities budget | Built in to the annual Precept received from CCBC | Provide a budget to Trefriw Outdoors for refreshments, etc. Church Service and Lighting up Event to be agreed for December. | October 2026
Community Skips
Provide community access to skips to remove bulky items free of charge | Approx £730 for a skip, skip licence and support from Crest to take electrical and other specific items | No budget provision for 2026/27 although unallocated reserves could be used | Following CCBC's withdrawal of the community skip services, enquiries made with commercial providers and quotes obtained. However, due to the substantial uplift in costs and restrictions imposed on the items that could be disposed of, members made a decision on 10th September 2024 that the cost and conditions were not viable and the no skip would be provided for 2024/25. The situation will continue to be reviewed periodically to see whether there is scope to reintroduce any form of community skip | Ongoing - Clerk to liaise with other T&CCs who continue to provide a periodic community skip to understand how this is working in practice
Defibrillators
Inspect village defibrillators on behalf of the Welsh Ambulance Service | Reserve being built up to fund replacement pads and batteries. Budget of £200 allocated in 2026/27 to cover costs of new pads, (£600 held in allocated reserves) | Built in to the annual Precept received from CCBC | Quarterly checks, last check undertaken in April 2026. New pads to be installed in all devices during 2026. | Routine quartely checks to take place in July / October / January / April
Footpath Maintenance
Maintain and improve designated footpaths within the community ensuring good performance from contractors | Budget of £1,250 allocated For 2026/27 | Built in to the annual Precept received from CCBC (anticipated part reimbursement from CCBC of not less than £1,000 ) | Tender undertaken in Nov/Dec 2021 - new contract awarded from 1st April 2022 for three years with potential to extend for a further two year period if agreeable to TCC and existing contractor. To be reviewed September 2024. Agreement reached with incumbent contractor to continue with existing contract until March 2027 | October 2026
Grants and Donations
Receive requests for support to local and national organisations | Budget of £500 allocated for 2026/27 | Built in to the annual Precept received from CCBC | Applications for grants are considered bi-annually in June and December, with requests that benefit the local community being given priority. | June 2026
Mine workings effluent
Work with NRW and other bodies to identify and control effluent from mineworkings in the Gwydir Forest | N/A | N/A | Work with appropriagte bodies as necessary. | Ongoing
Notice Boards
Keep Trefriw and Llanrhychwyn Community Council notice boards in good condition | TBC | As necessary from annual Precept received from CCBC and/or Reserves | Ensure that noticeboards are kept in a good condition to provide information for residents. Visual maintenance check and clean every 6 months. | June 2026 and January 2027
Outdoor Spaces and footpaths
Maintain open spaces and footpaths, working with CCBC, NRW, Trefriw Outdoors and Eryri National Park as necessary | TBC | Ongoing | Inspect and maintain as necesssary. | Ongoing
Parking
Parking in and around the village monitored by TCC and CCBC Highways in consultation with the community | N/A | N/A | Work with CCBC to manage and remove dangerous and inconsiderate parking, including Highways installing yellow lines. | Ongoing
Planning Applications
Planning applications received from CCBC and Snowdonia National Park for comment | No | Not applicable | Consider and respond to all planning applications as formally notified by CCBC or SNPA. | As required
Recreation Fields
Maintain condition of recreation fields | To be taken from overall General Village Maintenance budget of £1,518 as allocated in 2026/27 budget | Built in to the annual Precept received from CCBC | Grass cutting as required between April and October. | As scheduled
Support Village Improvements, Local Events and Initiatives
Work with groups and individuals to improve the village environment including community gardens/spaces, tackling litter and dog fouling, etc. | Possibly - see grants and donations | Possibly from grants and donations, or other grant funding when possible | Work to firm up plans and costs, and source grant funding wherever possible. | As required
Swingfield and Playpark Trust
Provide representation to the Board of Trustees for the Children's Playing Field, Trefriw Charity (505387) | No | N/A | Currently Cllrs Jasmine Kelly and Idris Bowen. | As required
Town and Community Council Forum
Attend local Clerk and Councillor forum meetings | Travel expenses if claimed £50 allocated for 2026/27 | Built in to the annual Precept received from CCBC | Clerk and Chair attend regular meetings of the Forum to meet with CCBC and other colleagues, to share best practice and stay informed. | As required
Trees on TCC Land
Manage the condition of the trees on TCC land (excluding the cemetery - see above) | Budget of £2,000 allocated for general tree safety work to include ash dieback for 2026/27; in addition, £1,520 held between allocated reserve and deposit account | Built in to the annual Precept received from CCBC | Tree Maintenance Working Group set up to monitor and report back to full council. | Ongoing
Village Hall
Set community working days to improve the village hall | Cost of materials as necessary | Built in to the annual Precept received from CCBC | Clean and repair as necessary in conjunction with community members, not less than every 12 months | As required
War Memorial
Maintain the condition of, repair and protect the war memorial | Periodically | As necessary from the annual Precept received from CCBC | Monitor condition of the war memorial, taking advice from the War Memorials Trust | Next review July 2026
Work with the community garden club to manage the war memorial gardens | Grant allocated to the garden club annually upon request | Built in to the annual Precept received from CCBC | Liaise with community garden club members | Ongoing
Provide an annual wreath and provide representation at the annual Memorial Services | Part of Donations budget allocated for 2026/27 | Built in to the annual Precept received from CCBC | Participate in the annual Remembrance Sunday service and present a wreath on behalf of the community Wreath to be ordered from British Legion, Llanrwst - collection during October 2026 in readiness for Remembrance Services on 8th November 2026 | October 2026
Website Maintenance
Maintain as far as possible a bi-lingual website. Support a co-ordinated approach to website information and promote Trefriw wider afield | Costs as necessary | As necessary from Reserves | Work towards improving upon a bilingual website | Ongoing

## Live Projects
Trefriw Community Council Community Plan for the year 2026/27
Our vision is to make Trefriw a great place to live, work and visit
Village Projects
Target for completion | Partners and/or Advisors | Actions completed to date | Further actions and timescales | Project cost to TCC | Funding stream | Ongoing action
TREE MAINTENANCE WORKING GROUP (FORMERLY ASH DIEBACK WORKING GROUP)
2027 | * Jay Butters | * Inspection of all ash trees on TCC land * Action plan to deal with ash dieback works identified, prioritised over a 7 year programme of works | * Identify ash trees on TCC land where there is responsibility to manage * Commence works identified as necessary | TBC | Combined budget of £2,000 allocated for 2026/27 tree safety work, including ash dieback. In addition, £1,520 held between allocated reserve and deposit account | Continue 7 year plan to manage trees infected with the ash die-back virus
CEMETERY EXTENSION WORKING GROUP
Stage 1 complete |  | * Purchase of land for extension of the current cemetery. * Form a cemetery working group (CWG) * Planning permission granted 2018 and then amended in 2023 * Works to provide ramp access into extension through existing wall completed 2025 Spring 2025 - Community Engagement event held with paper and online questionnaire to seek residents' views on use of cemetery extension land. Pupils at Ysgol yr Enfys submitted some ideas of how they envisage the cemetery extension looking | * Seek grant funding to meet any future project costs beyond land purchase. * Hedging for perimeter secured through Conwy Community Keyfund at no cost to TCC. Planted by community groups Spring 2025. | * Loan of £10,000 for land purchase/cost of works to complete extension. Annual repayments being made | * Loan repayments built in to the annual Precept received from CCBC * Remaining Capital Reserve of £6,675 held to offset project costs | * Final loan repayment made in March 2026 * Consult with community to agree use of cemetery extension. * Pupils at Ysgol Dyffryn yr Enfys primary school to include a cross-curricular project to produce their design ideas for the cemetery extension. This project will be guided by feedback from our 2025 community engagement event. To include garden, seating, and areas for burials and ashes. Pupils invited to submit their design ideas during the September school term for judging in the new year, with work on the garden planned to begin in spring 2026. * Go to tender to complete works to bring the cemetery extension into use.
COMMUNITY ENGAGEMENT
Ongoing |  | * "Meet your Councillor" sessions combined with monthly Community Coffee Mornings * 2022/23 Autumn Winter Community Engagement event held, together with paper and online questionnaire * Spring 2024 Community Engagement event held with paper and online questionnaire * Spring 2025 Community Engagement event held in the village hall, with paper and online questionnaire also available | * Arrange and/or support a range of activities/events within the community to raise funds for village enhancements, including the village hall. Some suggestions already made include: film nights, bingo nights, Welsh concert, auction of promises, gin/beer and dance evening, childrens' fun day, amateur dramatics. * Consider ways in which young people can be involved in community Council decision making, for example a "shadow Council". * Undertake consultation with children and young people to identify activities and events, etc. Develop activities and events to involve children and young people e.g. Halloween workshops, Christmas Tree/Santa event, etc. Support village groups in encouraging children and young people to take part in activities and events. | TBC | Seek potential grant funding as identified | * Set up and support working groups for events. * Continue monthly coffee mornings in Village Hall
|  |  | Continue to work with Trefriw Outdoors (formerly Walkers are Welcome), including arranging an event for local businesses to develop further ideas | Possibly - see grants and donations |  | Actively support local events to promote the village and the community
|  |  | Maintain and develop the partnership with Trefriw Outdoors / Trefriw Walking Festival to develop further events e.g. annual Trefriw Walking Festival, maintain and develop the Trefriw Trails | Possibly - see grants and donations | Built in to the annual budget, in part offset by monies received from CCBC | Work in partnership to develop and plan events
SERVICES AT RISK WORKING GROUP - PLAYPARKS AND PUBLIC TOILETS |  |  | CCBC have advised that certain services are at risk of being lost to the community. Transfer of Assets to the community has previously been suggested, or financial contributions being requested from the community. Further updates awaited from CCBC
PLAYPARKS
Ongoing |  | January 2020 Residents' consultation meetings February 2020 Services-Assets working group set up | 2021 * Continue dialogue with CCBC to ascertain what financial contributions might be required for play equipment repair/replacement as necessary. * Make recommendations to full council for consideration. | To be ascertained | * Cumulative amount of £13,702 held in Reserves as at 14/05/2026 - additional sum of £1,000 in 2026/27 budget to continue to build reserve | Continue dialogue with CCBC as information is made available
PUBLIC TOILETS
Ongoing |  | January 2020 Residents' consultation meetings February 2020 Services-Assets working group set up Spring 2025 - Community Engagement event held with paper and online questionnaire to seek residents' views on the future use of the public toilets | 2021 * Continue dialogue as possible with CCBC to ascertain what financial contributions might be required to maintain opening of public toilets * Make recommendations to full Council for consideration. 2025 * Discussions ongoing with CCBC to identify options available to the community. Recent community consultation had mixed views on whether to retain the toilets at community cost, or have them closed by CCBC. 2026 * An all-abiity Portaloo trialled but not deemed suitable for needs so currently no public toilet provision. | 2024/25 - £1,265 paid over to CCBC as a 10% contribution towards revenue costs 2025/26 - Agreement made with CCBC that TCC would cover all revenue costs to enable seasonal opening, £8313. 2025/26 and 2026/27- Costs of Portaloo trial, £275.50 | * Cumulative amount of £5,990 held in Reserves and deposit account as at 31/03/2026. * Additional sum of £2,000 in 2026/27 budget to continue to build reserve * Seek potential for grant funding
VILLAGE IMPROVEMENTS
VILLAGE SEATING AREAS
Ongoing |  | May 2020, May 2022 & May 2024 Repair as necessary and repainting of village seating areas | * Periodic reviews of condition, and works as required. 2026 * * Obtain costs to replace all village seating with maintenance-free plastico material. Grant funding being sought for this project. | Nil | Cost of materials previously reimbursed by CCBC. Potential Grant Funding | Annual visual check and further maintenance as required
PLAYPARK EQUIPMENT
Ongoing |  | Condition of play equipment at the two village play parks inspected annually through CCBC | Investigate costs to repair existing, or source funding to install replacement play equipment in the Childrens Play Park on Gower Road | TBC | Possible grant funding, TBC
VILLAGE HALL WORKING GROUP
Ongoing |  | Feb 2020 - Form a Village Hall working group (VHWG) April 2022 and 2024 - Revised hall charging schedule and hire contract agreed by TCC Spring 2025 - Community Engagement event held in the village hall, with paper and online questionnaire to seek residents' views on the future use of the Village Hall | * Ongoing development of a marketing strategy to maximise use of the Village Hall and therefore income, including bookings management. * Community consultation identified that there is support for the village hall to remain. The major issue identified was inefficient heating. Investigate improvements to the building including the potential for improved heating. Other improvements to be identified. All proposed changes to be approved by the CCBC Listing Officer. | To be identified | To be identified | Investigate improvements identified and seek grant funding to carry out works.

## Completed Projects
Trefriw Community Council Community Plan
Our vision is to make Trefriw a great place to live, work and visit
Village Projects Completed
Completion Date | Partners and/or Advisors | Actions completed to date | Project cost to TCC | Funding stream
LLANRWST NORTH PLATFORM SIGNAGE TO INCLUDE TREFRIW
Completed 2025 |  | February 2024 Agreement reached for signage to be installed by TfW at North Llanrwst station to advise passengers to alight for Trefriw, subject to funding being available September 2024 Confirmation received that signage to be changed to read "Llanrwst North and Trefriw" with costs to be met by Transport for Wales March 2025 New bilingual boards installed to indicate that the station is also the stop for Trefriw | Nil | Transport for Wales
PLAYPARKS
Completed 2024 | Childrens Playpark Trustees | July 2024 Accessible roundabout installed with 90% of costs met by grant funding December 2024 Installation of additional equipment: MagPost scientific magnifying glass for sensory play Log rack for parking bikes and scooters | £865 (5% contribution towards grant funding received) | UKSPF Conwy Community Regeneration Key Fund
VILLAGE IMPROVEMENTS
REPLACEMENT OF HISTORIC PLACES OF INTEREST SIGN
Completed 2024 |  | October 2024 Installation of replica sign | Nil | UKSPF Voluntary Sector Key Fund
CYCLE STANDS
Completed 2023 |  | February 2023 Installation of 2 planter-type cycle stands in the Singrig garden area | £327.34 (20% contribution towards grant funding received) | (EAFRD) Wales Rural Development Programme 2014 - 2020 RDP Scheme: LEADER – Rural Community Development Grant
VILLAGE SEATING AREAS
Completed 2022 |  | December 2022 Installation of an accessible picnic bench in the community field | £327.34 (20% contribution towards grant funding received) | (EAFRD) Wales Rural Development Programme 2014 - 2020 RDP Scheme: LEADER – Rural Community Development Grant
BUS STOPS
Completed 2025 |  | Spring 2025 Bus stop opposite the Trefriw Woollen Mill painted to cover graffiti | £53.73 for paint while works were carried out by volunteers | N/A